CDM Modernization

We are modernizing a legacy batch ecosystem onto Amazon Web Services with a clear target-state across ETL, orchestration, and runtime. The modernization is delivered in two primary waves (Investors first, Advisers second), with additional non-ETL job categories executed in parallel and integrated during SIT/UAT.

Target-state architecture

1) ETL modernization

- Convert Informatica PowerCenter XML assets (workflow + mapping) into PySpark jobs

- Conversion approach:

  - Automated baseline conversion using LTIMindtree utility tool

  - Mandatory manual completion to achieve 100% functional equivalence

  - Standardized framework: config-driven design, audit/control layer, reusable read/write utilities

2) Orchestration modernization

- Migrate orchestration from AutoSys to Apache Airflow

- Airflow will manage:

  - dependency chaining and job sequencing

  - schedules/calendars and event triggers

  - alerts, SLAs, retries, failure handling

  - rerun/backfill strategies

  - concurrency controls (e.g., 10 parallel pipelines)

3) Runtime modernization — decision dependency (Option A vs Option B)

Option A: Databricks + Airflow

- Pros: managed Spark runtime, standardized job execution, strong operational tooling

- Typical integration: Airflow triggers Databricks Jobs; data lives on S3/Delta

Option B: Amazon Elastic Kubernetes Service (Spark on K8s) + Airflow

- Pros: full control over runtime, consistent Kubernetes operational model

- Typical integration: Airflow triggers Spark on K8s submit wrappers / K8s operators

✅ Critical note:
The Option A vs Option B decision impacts infrastructure setup, CI/CD packaging model, logging/monitoring approach, job submission templates, and performance tuning standards. Therefore, the runtime choice must be finalized early (Phase 0/Phase 1) so the “conversion factory” doesn’t build incompatible job wrappers.

Delivery split (two primary waves/modules)

Wave 1 — Investors

- 207 ETL components plus their orchestration chain

- Goal: establish the conversion factory, lock standards, prove end-to-end equivalence

Wave 2 — Advisers

- 597 ETL components plus their orchestration chain

- Goal: scale throughput using proven factory patterns and automation

Parallel non-ETL rewrites

These tracks proceed in parallel but must be integrated and validated end-to-end during SIT/UAT:

- Python scripts: file arrival checks, alerts, IDQ checks, operational validations

- SaaS API rewrites: publish/report jobs, golden/cross-ref sources

- MDM SaaS jobs: stage loads, lookups, tokenization, match & merge

- Manual AutoSys commands: events, global variables, status checks, control utilities

Current state vs target state orchestration

Current state (today)

Orchestration is implemented in AutoSys, and job streams typically execute a combination of:

- Informatica workflow invocations (command-line driven, parameterized)

- Shell scripts (pre/post steps, file checks, variable handling, notifications)

- Control jobs (events, global vars, dependency checks, rerun/hold logic)

Therefore, orchestration truth is not only in Informatica XML — it exists in:

- AutoSys

- shell scripts

- global variables

- calendars

- triggers

- runtime behaviour

- run history

Target state (future)

Orchestration will be implemented in Airflow, where each legacy AutoSys chain becomes one or more DAGs:

- Tasks mapped to:

  - Spark ETL jobs

  - Python/script tasks

  - API/MDM tasks

  - control/notification tasks

- Behaviour equivalence required for:

  - schedules/calendars

  - event triggers

  - retries/failure handling

  - alerts/escalations

  - rerun/backfill strategy

Mandatory prerequisite:
Before building correct Airflow DAGs, we must fully understand how AutoSys currently calls:

- Informatica workflows/sessions

- shell scripts and how calendars, triggers, variables, and failure logic govern execution.

Execution timeline and key activities

Phase 0 — Infrastructure setup & prerequisites (Foundation)

Key outcomes

- SIT/UAT environments ready:

  - AWS account setup, VPC/network, Group and entitlement approvals

  - Storage (S3 zones), compute (Databricks/EKS), security baselines, airflow access

- Access readiness:

  - IAM roles/policies, secrets management, repo access, CI/CD access

- Standard templates and baselines:

  - PySpark job template + config model

  - Airflow DAG template + alerting standards

  - logging/monitoring baseline (metrics + logs + failure notifications)

Target DB instance setup (explicit dependency)

Target database infrastructure must be available early:

- target DB instance provisioning (for SIT/UAT at minimum)

- network connectivity, credentials in secrets manager

- schemas/tables readiness strategy (create vs migrate)

- standard write patterns (overwrite/merge/upsert rules)

PowerCenter dev/compare environment + test data (explicit dependency)

To validate PySpark equivalence, we require:

- a stable PowerCenter dev/compare environment

- appropriate test datasets that can be processed by both:

  - legacy Informatica workflows/mappings

  - new PySpark pipelines

- a repeatable runbook to generate legacy outputs for reconciliation

Without this, “100% conversion” cannot be proven, because reconciliation evidence will be incomplete or inconsistent.

“Platform Ready” sign-off No conversion should fully test until:

- Runtime option is decided (A or B)

- Access + CI/CD + logging baseline is ready

- Target DB for SIT/UAT is available (at least initial)

- PowerCenter compare env + test data plan is ready

Phase 1 — Inventory assessment & design (Discovery + standards)

1A) Inventory confirmation (AutoSys + Informatica)

AutoSys inventory

- jobs, box jobs, calendars, triggers, dependencies

- global variables, events, alerts, exit codes

- execution history + failure patterns

Informatica inventory

- workflows/mappings XML list

- sources/targets, lookups, transformations, parameter files

- workflow assumptions (often controlled by AutoSys scheduling)

1B) Complexity classification (conversion sizing)

Classify mappings:

- Simple / Medium / Complex / Very Complex
Based on:

- number of sources/targets, joins/lookups

- update strategy, merges, sequencing rules

- expressions, dynamic SQL

- mapplets/reusable logic, workflow-driven behavior

1C) Migration design & standards

Airflow standards

- DAG patterns, naming, retries, SLAs

- calendars vs event triggers mapping

- notifications/escalations

- parameter strategy

- concurrency model (pools/queues)

PySpark standards

- config-driven design

- reusable utilities (readers/writers/audit/DQ)

- error handling and controls framework

Testing & reconciliation standards

- row count, key checks, null checks

- evidence templates

- defect lifecycle and sign-off criteria

Gate 1 (must-pass)

“Conversion Factory Rules Frozen”
Standards are finalized and approved to avoid rework across waves.

Phase 2 — Build & conversion (Automated + manual finalization)

2A) ETL conversion factory: Informatica XML → PySpark jobs

We generate baseline code via LTIMindtree utility tool and follow a strict manual completion + validation loop.

Per-mapping execution loop (target = 100% conversion)

- Ingest mapping/workflow XML as source-of-truth

- Auto-convert → baseline PySpark + config scaffold + conversion report

- Mandatory manual completion:

  - fix column mismatches (SQL vs DF)

  - datatype alignment and casting rules

  - correct joins/filters + null semantics

  - complete unhandled/partial transformations

- Unit testing readiness:

  - define test cases, expected metrics, reconciliation rules

- Execute unit tests:

  - row counts, null checks, key checks

  - reconciliation vs PowerCenter outputs

- Push to CI/CD:

  - linting, packaging, unit checks, code review gates

- Deploy to SIT runtime (Option A or B)

- Generate reconciliation evidence for sign-off

- Promote to UAT after defect closure + regression pass

✅ Critical dependency:

- PowerCenter compare env + test data must be stable

- target DB (or target storage) must be ready to validate end-to-end writes

2B) Orchestration migration factory: AutoSys → Airflow DAGs (currently in AutoSys)

ETL conversion alone does not guarantee production success; orchestration defines execution order, triggers, calendars, and operational behavior.

Step 1 — Understand existing AutoSys behavior (mandatory)

We must analyze:

- how AutoSys invokes Informatica workflows/sessions (commands, params)

- how shell scripts participate (pre/post/control logic)

- dependency rules (calendars, triggers, exit conditions, reruns)

- runtime behavior from logs/history (actual execution order, hotspots)

Step 2 — Design Airflow DAG strategy

- DAGs organized by workflow groups (Investors/Advisers), not 1 DAG per job

- standard DAG template with:

  - pools/queues for concurrency (10 parallel pipelines)

  - SLA + alerting + escalation

  - calendar/trigger equivalents

  - environment parameterization (SIT/UAT/PROD)

  - rerun/backfill strategy

Step 3 — Implement and validate orchestration

- DAG unit tests (dependency logic)

- SIT chain validation (end-to-end schedule equivalence)

- failure injection tests (retry/alert correctness)

Phase 3 — SIT, UAT & production readiness (hardening)

SIT focus

- dependency correctness (triggers, retries, calendars)

- end-to-end execution + reconciliation vs legacy

- evidence generation for each run

UAT focus

- business functional equivalence sign-off

- defect triage + fixes + regression cycles

- operational readiness:

  - monitoring dashboards

  - runbooks

  - support + escalation model

Cutover readiness

- freeze window plan

- deployment and rollback steps

- approvals and go/no-go checklis

Phase 4 — Production rollout & warranty

- production release + post-deployment validation

- warranty support during stabilization

- operational handover:

  - final acceptance

  - runbook sign-off

  - transition to steady-state support