MVP Implementation Plan – AI Coding & Low-Level Design Platform

MVP Scope

In this MVP, we will focus only on two major capabilities:

- Coding Step Automation

  - Generate application code based on user requirements.

  - Allow users to review and modify generated code.

  - Support basic application execution in a sandbox environment.

- Low-Level Design Generation

  - Generate module-level design.

  - Generate component structure.

  - Generate API-level and file-level design.

  - Provide basic design documentation for developers.

Out of scope for this MVP:

- Full SDLC automation

- Production-grade deployment automation

- Enterprise governance workflow

- Advanced multi-agent orchestration

- Complete CI/CD automation

High-Level MVP Timeline

Phase 1: MVP Architecture

Timeline: 24 June – 1 July

Objective

Define the complete MVP architecture, system boundaries, technology stack, and high-level component interaction.

Activities

- Define MVP scope and assumptions.

- Prepare high-level architecture.

- Identify required GCP services.

- Define frontend, backend, LLM, RAG, sandbox, and storage components.

- Integration of NIKBOT and NIKRAG system (Trained RAG Agents for coding automation)

- Define data flow between UI, application services, LLM services, and sandbox.

- Prepare technical architecture diagram.

- Finalize security and access-control approach.

Deliverables

- MVP architecture document

- High-level system design

- Component interaction diagram

- Initial GCP service mapping

Phase 2: UI/UX Design

Timeline: 29 June – 10 July

Objective

Design the user interface for creating projects, entering requirements, generating design, generating code, and reviewing outputs.

Activities

- Design landing/dashboard page.

- Design project creation flow.

- Design requirement input screen.

- Design low-level design output screen.

- Design coding workspace with file explorer, editor, AI assistant, and preview panel.

- Design sandbox execution output screen.

- Prepare clickable UI prototype.

Deliverables

- UI wireframes

- UX flow

- Clickable prototype

- Final screen designs

Phase 3: API Integration for Application Services

Timeline: 13 July – 24 July

Objective

Develop backend APIs required for project management, requirement processing, design generation, code generation, and file handling.

Activities

- Create project management APIs.

- Create requirement submission APIs.

- Create low-level design generation APIs.

- Create code generation APIs.

- Create file create/read/update/delete APIs.

- Create execution request APIs.

- Create API contracts between frontend and backend.

- Integrate frontend with backend services.

Deliverables

- Backend application APIs

- API specification document

- Frontend-backend integration

- Basic project and file management working flow

Phase 4: Infrastructure Services for Application

Timeline: 27 July – 31 July

Objective

Set up the required GCP infrastructure to host and run the MVP application.

Activities

- Set up GCP project and environment.

- Configure Cloud Run or GKE for backend services.

- Configure Cloud Storage for generated code and artifacts.

- Configure Firestore or Cloud SQL for metadata.

- Configure Secret Manager for API keys and credentials.

- Configure Cloud Logging and Monitoring.

- Set up basic IAM roles and access policies.

Deliverables

- GCP infrastructure setup

- Application hosting environment

- Storage and database setup

- Logging and monitoring setup

- Secure secret management

Phase 5: LLM and RAG Integration

Timeline: 1 July – 7 August

Objective

Integrate Gemini LLM and RAG layer to support requirement understanding, low-level design generation, and code generation.

Activities

- Integrate LLM API.

- Create prompt templates for low-level design generation.

- Integration with NIKRAG system for validate templates and workflows

- Create prompt templates for code generation using NIKBOT.

- Create RAG knowledge base for coding standards, templates, architecture patterns, and project guidelines.

- Implement context retrieval for relevant design and coding inputs.

- Validate LLM output quality.

- Add guardrails for prompt length, token usage, and response validation.

Deliverables

- Gemini API integration

- NIKBOT Integration

- RAG pipeline

- Prompt templates

- LLD generation flow

- Code generation flow

- Token and cost-control mechanism

Phase 6: Sandbox Creation

Timeline: 27 July – 7 August

Objective

Create a execution environment where generated application code can be executed and validated.

(here we required cloud account which having root level permission )

Activities

- Design sandbox execution architecture.

- Create isolated runtime environment for generated code.

- Configure CPU, memory, timeout, and file-size limits.

- Enable basic execution for selected technology stack.

- Capture execution logs and errors.

- Return execution result to frontend.

- Implement sandbox cleanup after execution.

Deliverables

- Sandbox runtime

- Code execution service

- Execution logs

- Error output display

- Runtime security controls

Final MVP Demo Flow

- User logs into the platform.

- User creates a new project.

- User enters application requirement.

- System generates low-level design.

- User reviews the design.

- System generates application code.

- Generated files are displayed in the coding workspace.

- User can edit the generated code.

- User runs the code in sandbox.

- System shows execution logs and output.

- User can review the final generated application/code.

MVP Success Criteria

The MVP will be considered successful if we can demonstrate:

- Requirement-to-low-level-design generation

- Low-level-design-to-code generation

- Editable coding workspace

- sandbox execution

- Basic project and file management

- LLM and RAG-based generation workflow

- End-to-end demo from requirement input to executable code